## Sheet1
| 2021 |  |  |  |  | 2022 | [11 empty] | 2023
Milestones | ToR | Sep | Okt | Nov | Dec | Jan | Feb | Mar | Apr | Maj | Jun | Jul | Aug | Sep | Okt | Nov | Dec | Jan | Feb | Mar | Apr | Maj | Jun | Jul | Aug | Sep | Okt | Nov | Dec
review progress and plan (WG) | d | WG | [23 empty] | WG | bar: Sep
package repo set-up | c |  | x
createRDBESrawObj and aux functions; migrate to package | a |  | x
createRDBESprepObj and aux functions; migrate to package | a |  |  | x
define createDBestim | a |  |  |  | x
createDBestim and aux functions; migrate to package | a |  |  |  |  | x
define overviews and reports | a | [5 empty] | x (a,b)
createDBoverviews/reports and aux functions; migrate to package | a | bar: Jun
package published (in production) | c | [24 empty] | x | bar: Jun; Sep
improve estimation and overview/report code and options | a | [21 empty] | x |  |  | x | bar: Jun; Sep to 2023 Feb
review and improve documentation (rOxygen2) | c | [24 empty] | x | bar: Sep
evaluate TAF perspective | e | [24 empty] | x | bar: Sep
recommend on developments of the data model | b | [24 empty] | x | bar: Sep
discuss package mantainence | c | [24 empty] | x | bar: Sep; Dec
final report | [25 empty] | x
report to wgcatch | d |  |  | x | [23 empty] | x | bar: Nov
report to wgrdbes gov | d,e |  |  |  | x | [23 empty] | x | bar: Dec
(a) with RCG subgroup fisheries overviews
(b) fishnCo data quality